## Sheet1
DEFECT TRACKING LOG | [9 empty] | DEFECT TRACKING LOG
PROJECT NAME | ICTAK ALUMNI JOB PORTAL
WEB SITE | https://delightful-earrings-fish.cyclic.app/
PURPOSE | To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase,
but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation
of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress.
DEFECT ID | DATE CREATED | MODULE NAME | DESCRIPTION | RAISED BY | ASSIGNED TO | STATUS | SEVIORITY | ENVIRONMENT | SCREENSHOT
IAJP-76 | 19/02/2023 | VISITOR | The Apply button in the main page is visible only at some times. | HASNA | DEVELOPER | OPEN | MEDIUM | Windows 10 andabove Chrome browser,Edge and Safari | https://drive.google.com/file/d/1uDrtPDpa0biW0XmQJhd2lYqwmzNNoOB9/view?usp=share_linkhttps://drive.google.com/file/d/18I9JSOpsmzAIsCrZ32ywJW4EDyQge9T2/view?usp=sharing
IAJP-64 | 19/02/2023 | VISITOR | Page buffers when enter any keywords in the search bar that doesn't exists on any available jobs | SABU SEBASTIAN | DEVELOPER | OPEN | MAJOR | Windows 10 and above Chrome browser, Edge and Safari
IAJP-82 | 19/02/2023 | ADMIN, ALUMNI | Input fields in the sign up page of admin module accepts only the inputs with minimum of five characters. | DEEPTHI | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser, Edge and Safari | https://drive.google.com/file/d/1E8sPI4av_-joYrvF9TbaChvDL7UKLaII/view?usp=share_link
IAJP-81 | 22/02/2023 | ADMIN | Admin cant login to the application with the credential provided. | SWATHI KRISHNA | DEVELOPER | OPEN | CRITICAL | Windows 10 and above Chrome browser, Edge and Safari | https://drive.google.com/file/d/16lqH0x0OS2TIp_eJLmsi6wCU-pUzrKFT/view?usp=share_link
IAJP-73 | 22/02/2023 | ADMIN | The username field in signup page requires minimum 5 characters and it accepts digits and special characters. | AYISHA | DEVELOPER | OPEN | COSMETIC | Windows 10 and above Chrome browser,Edge and Safari | https://drive.google.com/file/d/1eVYEiU44L3qD3o6OzdwPdr_R7yfnnIN_/view?usp=share_link
IAJP-71 | 22/02/2023 | ADMIN | Job experience field accepts only the input values with minimum of 3 letters | AYISHA | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser,Edge and Safari
IAJP-68 | 22/02/2023 | ADMIN | The age field accepts only inputs with minimum of five letters. | AYISHA | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser,Edge and Safari
IAJP-39 | 22/02/2023 | ALUMNI | The view posts read more page in the Alumni role doesn't have page close button to navigate to the home page. | SABU SEBASTIAN | DEVELOPER | OPEN | COSMETIC | Windows 10 and above Chrome browser,Edge and Safari
IAJP-48 | 22/02/2023 | ALUMNI | Drop down list for selecting course name and placement status is not present. | HASNA | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser,Edge and Safari | https://drive.google.com/file/d/1SRhhOYhp52pf2WM_q1SZhViKLOYoqCvS/view?usp=share_link
IAJP-49 | 22/02/2023 | ALUMNI | Field for providing company name (if placed ) is not present. | HASNA | DEVELOPER | OPEN | MAJOR | Windows 10 and above Chrome browser,Edge and Safari | https://drive.google.com/file/d/1KSLZU27kv_Sz74Sp94Suptn87NEosBNu/view?usp=share_link
IAJP-56 | 22/02/2023 | ALUMNI | The page is started buffering sometimes when clicking on the read more option . | SABU SEBASTIAN | DEVELOPER | OPEN | MAJOR | Windows 10 and above Chrome browser,Edge and Safari
IAJP-65 | 22/02/2023 | ALUMNI | The Submit button is disabled when leaving 'If Then Enter Placed Company Name' field blank in apply job functionality. | SABU SEBASTIAN | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser, Edge and Safari
IAJP-67 | 23/02/2023 | ALUMNI | The user can submit application many times for the already applied jobs.(Button is not disabled for the already applied jobs). | SABU SEBASTIAN | DEVELOPER | OPEN | COSMETIC | Windows 10 and above Chrome browser, Edge and Safari
IAJP-66 | 23/02/2023 | ALUMNI | Input fields in the job apply page accepts invalid data . | SABU SEBASTIAN | DEVELOPER | OPEN | MAJOR | Windows 10 and above Chrome browser, Edge and Safari
IAJP-55 | 23/02/2023 | EMPLOYER | Login page shows the registration page. | AYISHA | DEVELOPER | OPEN | COSMETIC | Windows 10 and above Chrome browser, Edge and Safari
IAJP-63 | 23/02/2023 | EMPLOYER | The job name ,location,job type ,qualification and language fields in the apply job and edit job page accepts invalid datas. | HASNA | DEVELOPER | OPEN | COSMETIC | Windows 10 and above Chrome browser, Edge and Safari
IAJP-72 | 23/02/2023 | EMPLOYER | Submit button in the apply job and edit job page is getting enabled with invalid datas. | HASNA | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser, Edge and Safari
IAJP-77 | 24/02/2023 | FACULTY | The name field accepts only data with minimum of five letters. | SWATHI KRISHNA | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser, Edge and Safari | https://drive.google.com/file/d/1yUkHqEq08Csm_FsH5m3WAKYfV97o6jWD/view?usp=sharing
IAJP-57 | 24/02/2023 | FACULTY | Submit button is getting enabled when user submit invalid datas in the signup activity. | ARYA KRISHNAN | DEVELOPER | OPEN | MEDIUM | Windows 10 and above Chrome browser, Edge and Safari | https://drive.google.com/file/d/1u4zXaN_VwAmZzNjC9WKhiH4Ng9SCFNlH/view?usp=sharing
IAJP-78 | 24/02/2023 | FACULTY | Create new post page has no input fields. | ARYA KRISHNAN | DEVELOPER | DEVELOPER | MAJOR | Windows 10 and above Chrome browser, Edge and Safari | https://drive.google.com/file/d/1y91xmzrBZt5s0BV0RZOdyIOnrwNzgK_Z/view?usp=sharing