## Sheet1
REQUIREMENT TRACEABILITY MATRIX - ICT JOB PORTAL
PRPEARED BY | Group-4 | [8 empty] | BUSINESS REQUIREMENT IDs | DESCRIPTION
DESIGNATION | Tester | [8 empty] | BID01 | Sign Up and Login Modules for Alumni, Faculty, Employers, Admin.
DATE | 27/02/2023 | [8 empty] | BID02 | Students must be able to create a profile for themselves after logging in with required valid details
Total No. Of Business Requirements | 7 | [8 empty] | BID03 | Admins, Faculties, and Employers can create a job posting.
Total No. Of Test Cases | 52 | [8 empty] | BID04 | All Visitors of the web app can see Posting and Only registered Alumni can respond to Job Posting
[10 empty] | BID05 | Response to a Job Posting is a submission of a PDF file or Online Link.
REQUIREMENT TRACEABILITY MATRIX |  |  | BUSINESS REQUIREMENT ID's | [6 empty] | BID06 | A Job Posting Must have a Cut-off date and the response button should be automatically disabled after the cut-off time and date.
TEST SCENARIO ID | TEST SCENARIO DESCRIPTION | TEST CASE ID | BID001 | BID002 | BID003 | BID004 | BID005 | BID006 | BID007 | BID07 | Admins can verify the submissions to a post and forward it to the Employer / Post Owner.
TS_001 | Alumni Signup Page Validation | TC_01 | bar: BUSINESS REQUIREMENT ID's BID002
TC_02 | bar: BUSINESS REQUIREMENT ID's BID002
TC_03 | bar: BUSINESS REQUIREMENT ID's BID002
TC_04 | bar: BUSINESS REQUIREMENT ID's BID002
TC_05 | bar: BUSINESS REQUIREMENT ID's BID002
TC_06 | bar: BUSINESS REQUIREMENT ID's BID002
TC_07 | bar: BUSINESS REQUIREMENT ID's BID002
TC_08 | bar: BUSINESS REQUIREMENT ID's BID002
TC_09 | bar: BUSINESS REQUIREMENT ID's BID002
TS_002 | Alumni Login Page Validation | TC_10 | bar: BUSINESS REQUIREMENT ID's BID001
TC_11 | bar: BUSINESS REQUIREMENT ID's BID001
TC_12 | bar: BUSINESS REQUIREMENT ID's BID001
TC_13 | bar: BUSINESS REQUIREMENT ID's BID001
TC_14 | bar: BUSINESS REQUIREMENT ID's BID001
TS_003 | Verify New posts displaying on the alumni's profile | TC_15 | bar: BUSINESS REQUIREMENT ID's BID004
TS_004 | Verify job search functionality | TC_16 | bar: BUSINESS REQUIREMENT ID's BID004
TS_005 | Verify read more option of the posts displaying in the alumnis profile | TC_17 | bar: BUSINESS REQUIREMENT ID's BID004
TS_006 | Verify Alumini's Apply Job functionality with valid details | TC_18 | bar: BUSINESS REQUIREMENT ID's BID005
TC_19
TS_007 | Logut option verification | TC_20 | bar: BUSINESS REQUIREMENT ID's BID001
TS_008 | Employer Login Page Validation | TC_21 | bar: BUSINESS REQUIREMENT ID's BID001
TS_009 |  | TC_22 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0010 |  | TC_23 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0011 | Employer Sign Up Page Validation | TC_24 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0012 |  | TC_25 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0013 |  | TC_26 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0014 |  | TC_27 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0015 |  | TC_28 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0016 |  | TC_29 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0017 |  | TC_30 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0018 | Post a Job Page /Edit Form in View job page Validation of Employer with Valid Required Details. | TC_31 | bar: BUSINESS REQUIREMENT ID's BID003
TS_0019 | Post a Job Page /Edit Form in View job page Validation of Employer with Invalid Datas in Job Name, Location, Job Type, Qualification and Language Fields. | TC_32 | bar: BUSINESS REQUIREMENT ID's BID003
TS_0020 | Post a Job Page /Edit Form in View job page] Validation of Employer with some filed as blank. | TC_33 | bar: BUSINESS REQUIREMENT ID's BID003
TS_0021 | Post a Job Page /Edit Form in View job Page Validation of Employer with All filed as blank. | TC_34 | bar: BUSINESS REQUIREMENT ID's BID003
TS_0022 | View Job Page Validation of Employer | TC_35 | bar: BUSINESS REQUIREMENT ID's BID003
TS_0023 | Verify the approved posts listed on employers profile and verify the download resume options | TC_36 | bar: BUSINESS REQUIREMENT ID's BID003
TS_0024 | Verification of Logout functionality | TC_37 | bar: BUSINESS REQUIREMENT ID's BID001; BUSINESS REQUIREMENT ID's BID003
TS_0025 | Signup page validation of faculty with valid Details | TC_38 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0026 | Faculty Login Page Validation | TC_39 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0027 |  | TC-40 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0028 |  | TC-41 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0029 |  | TC-42 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0030 |  | TC-43 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0031 |  | TC-44 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0032 |  | TC-45 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0033 | Verify faculty create new post | TC-46 | bar: BUSINESS REQUIREMENT ID's BID003
TS_0034 | Verify logout page . | TC-47 | bar: BUSINESS REQUIREMENT ID's BID001
TS_0035 | Verification of ICTK Alumni job portal main page | TC-48 | bar: BUSINESS REQUIREMENT ID's BID004
TS_0036 | Verify search functionality in main page | TC-49 | bar: BUSINESS REQUIREMENT ID's BID004
TS_0037 | Verify Readmore functionality in main page | TC-50 | bar: BUSINESS REQUIREMENT ID's BID004
TS_0038 | Verify Apply functionality in main page | TC-51 | bar: BUSINESS REQUIREMENT ID's BID004
TS_0039 | Verify search functionality with job name field as blank | TC-52 | bar: BUSINESS REQUIREMENT ID's BID004

## Sheet2
ICT Alumni Job Portal
https://delightful-earrings-fish.cyclic.app/
Test Suite Name: ICTAK Alumni Job Portal -Alumni Page Verification
Version: | 1
Build: | 1
Dated: | 2023-02-17
Test Case id | TC_01
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni with Valid Required Details.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected . | Pass
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER NAME ON THE SIGNUP PAGE. | HASNA | User should able to type the valid name . | Same as expected. | Pass.
5 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address. | Same as expected. | Pass.
6 | ENTER VALID PHONE NUMBER | 1234567899 | User should able to type the valid phone number with 10 digits. | Same as expected. | Pass.
7 | SELECT COURSE NAME FROM THE DROP DOWN LIST. | FSD/DSA/ML-AI/RPA/ST/CSA | User should able to select the course name from the list. | User should not able to select the course name. Drop down list is not present. | Fail | BUG ID IAJP-48
8 | ENTER QUALIFICATION | BTECH | User should able to type the qualification. | Same as expected. | Pass.
9 | SELECT BATCH NAME FROM THE DROP DOWN LIST. | NORKA / KKEM / KDISC | User should able to select the batch name from the list | Same as expected. | Pass.
10 | SELECT PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to select their placement status from the list.. | User should not able to select the placement status Drop down list is not present. | Fail | Bug ID IAJP-48
11 | ENTER COMPANY NAME IF PLACED |  | User should able to type the company name. | User should not able to type the company name . Field is not present. | Fail | Bug ID IAJP-49
12 | ENTER VALID PASSWORD | 12AB@GH | User should able to type the valid password with atleast two characters,two digits and one special character. | Same as expected. | Pass.
13 | CLICK SUBMIT |  | User should get a message like data saved suuceesfully. | Same as expected. | Pass.
Test Case id | TC_02
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni with Invalid Name.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER INVALID NAME | H134A h@@@@ | User should able to type the invalid name and get an error message for entering invalid name. | Not as expected. Accepts data with minimum of two characters including digits and special characters. | Fail. | BUG ID IAJP-50
5 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address . | Same as expected. | Pass.
6 | ENTER VALID PHONE NUMBER | 9134567899 | User should able to type the valid phone number with 10 digits. | Same as expected. | Pass.
7 | SELECT COURSE NAME | FSD/DSA/ML-AI/RPA/ST/CSA | User shuld able to select the course name from the list. | Not as expected. | Fail | BUG ID IAJP-48
8 | ENTER QUALIFICATION | BTECH | User should able to type the qualification. | Same as expected. | Pass.
9 | SELECT BATCH NAME | NORKA / KKEM / KDISC | User should able to select the batch name from the list | Same as expected. | Pass.
10 | SELECT PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to select their placement status from the list.. | Not as expected. | Fail. | BUG ID IAJP-48
11 | ENTER VALID PASSWORD |  | User should able to type the valid password . | Same as expected. | Pass.
12 | CLICK SUBMIT |  | User should not able to submit their datas with invalid name. | Same as expected. | Pass.
Test Case id | TC_03
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni with Invalid Email Address.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass.
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER VALID NAME | Hasna | User should able to type the name . | Same as expected. | Pass.
5 | ENTER INVALID EMAIL ADDRESS | abcccgmail/com abcccAtgmail.com abccc@gmailcom abccc@gmail @gmail | User should able to type the invalid email address and get an error message for entering invalid email address. | Not as expected. Accept the data with minimum of two letters. | Fail | BUG ID IAJP-50
6 | ENTER VALID PHONE NUMBER | 9134567899 | User should able to type the valid phone numbe with 10 digits. | Same as expected. | Pass.
7 | ENTER COURSE NAME | FSD/DSA/ML-AI/RPA/ST/CSA | User shuld able to select the course name from the list. | Not as expected. | Fail | BUG ID IAJP-48
8 | ENTER QUALIFICATION | BTECH | User should able to type the qualification. | Same as expected. | Pass.
9 | ENTER BATCH NAME | NORKA / KKEM / KDISC | User should able to select the batch name from the list | Same as expected. | Pass.
10 | ENTER PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to select their placement status from the list.. | Not as expected. | Fail | BUG ID IAJP-48
11 | ENTER VALID PASSWORD |  | User should able to type the valid password . | Same as expected. | Pass.
12 | CLICK SUBMIT |  | User should not able to submit their datas with invalid email address. | Same as expected. | Pass.
Test Case id | TC_04
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni with Invalid Phone Number .
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass.
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER VALID NAME | Hasna | User should able to type the name. | Same as expected. | Pass.
5 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address . | Same as expected. | Pass.
6 | ENTER INVALID PHONE NUMBER | 1:qqqq 2:1234 | 1.User should not able to type the phone number with letters. 2.User should able to type the phone number with lessthan 10 digits. | 1.same as expected. 2.Not as expected. Accepts data with minimum of two digits. | Pass. Fail. | BUG IDIAJP-50
7 | SELECT COURSE NAME | FSD/DSA/ML-AI/RPA/ST/CSA | User shuld able to select the course name from the list. | Not as expected. | Fail. | BUG ID IAJP-48
8 | ENTER QUALIFICATION | BTECH | User should able to type the qualification. | Same as expected. | Pass.
9 | SELECT BATCH NAME | NORKA / KKEM / KDISC | User should able to select the batch name from the list | Same as expected. | Pass.
10 | SELECT PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to select their placement status from the list.. | Not as expected. | Fail. | BUG ID IAJP-48
11 | ENTER VALID PASSWORD |  | User should able to type the valid password. | Same as expected. | Pass.
12 | CLICK SUBMIT |  | User should not able to submit their datas with invalid phone number. | Same as expected. | Pass.
Test Case id | TC_05
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition.
Summary | Signup Page Validation of Alumni with Invalid Qualification Details.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass.
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER VALID NAME | Hasna | User should able to type the name. | Same as expected. | Pass.
5 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address with minimum of two letters. | Same as expected. | Pass.
6 | ENTER VALID PHONE NUMBER | 1234567899 | User should able to type the valid phone number. | Same as expected. | Pass.
7 | SELECT COURSE NAME | FSD/DSA/ML-AI/RPA/ST/CSA | User shuld able to select the course name from the list. | Not as expected. | Fail. | IAJP-48
8 | ENTER INVALID QUALIFICATION | B1T1E1C2H | User should able to type the invalid qualification and get an error message like qualification name should not contain digits. | Not as expected. Accepts data with minimum of two characters including digits. | Fail. | IAJP-50
9 | SELECT BATCH NAME | NORKA / KKEM / KDISC | User should able to select the batch name from the list | Same as expected. | Pass.
10 | SELECT PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to select their placement status from the list.. | Not as expected. | Fail. | IAJP-48
11 | ENTER VALID PASSWORD |  | User should able to type the valid password . | Same as expected. | Pass.
12 | CLICK SUBMIT |  | User should not able to submit their datas with invalid Qualification details.. | Same as expected. | Pass.
Test Case id | TC_06
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni with Invalid Password
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass.
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER VALID NAME | HASNA. | User should able to type the name. | Same as expected. | Pass.
5 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address | Same as expected. | Pass.
6 | ENTER VALID PHONE NUMBER | 1234567899 | User should able to type the valid phone number. | Same as expected. | Pass.
7 | SELECT COURSE NAME | FSD/DSA/ML-AI/RPA/ST/CSA | User shuld able to select the course name from the list. | Not as expected. | Fail. | BUG ID IAJP-48
8 | ENTER QUALIFICATION | BTECH | User should able to type the qualification. | Same as expected. | Pass.
9 | SELECT BATCH NAME | NORKA / KKEM / KDISC | User should able to select the batch name from the list | Same as expected. | Pass.
10 | SELECT PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to select their placement status from the list.. | Not as expected. | Fail. | BUG ID IAJP-48
11 | ENTER INVALID PASSWORD | 1234,'''' abcd | User should able to type the invalid password and get an error message like password must be strong and contains atleast 2 digis,3characters and one special character. | Not as expected. Accepts data with minimum of two characters. | Fail.. | BUG ID IAJP-50
12 | CLICK SUBMIT |  | User should not able to submit their datas with invalid password. | Same as expected. | Pass.
Test Case id | TC_07
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni with Already Registered Email address
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected.
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER VALID NAME | HASNA. | User should able to type the name. | Same as expected.
5 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the already registered email address and get an error message like email is registered already. | Same as expected. | Pass.
6 | ENTER VALID PHONE NUMBER | 1234567899 | User should able to type the valid phone number. | Same as expected. | Pass.
7 | SELECT COURSE NAME | FSD/DSA/ML-AI/RPA/ST/CSA | User shuld able to select the course name from the list. | Not as expected. | Fail. | BBBBUG ID BUG ID IAJP-48
8 | ENTER QUALIFICATION | BTECH | User should able to type the qualification. | Same as expected. | Pass.
9 | SELECT BATCH NAME | NORKA / KKEM / KDISC | User should able to select the batch name from the list | Same as expected. | Pass.
10 | SELECT PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to select their placement status from the list.. | Not as expected. | Fail. | BUG ID IAJP-48
11 | ENTER VALID PASSWORD | 1234,'''' abcd | User should able to type the valid password. | Same as expected. | Pass.
12 | CLICK SUBMIT |  | User should able to get an error message like email already exist. | Same as expected. | Pass.
Test Case id | TC_08
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni without selecting the Datas from drop down list.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected.
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | ENTER INVALID NAME | Hasna | User should able to type the name. | Same as expected. | Pass.
5 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address . | Same as expected. | Pass.
6 | ENTER VALID PHONE NUMBER | 1234567899 | User should able to type the valid phone number. | Same as expected. | Pass.
7 | NOT SELECTING COURSE NAME | FSD/DSA/ML-AI/RPA/ST/CSA | User should able to get an error message like please select one name from the list. | Not as expected. | Fail. | BUG ID IAJP-48
8 | ENTER QUALIFICATION | BTECH | User should able to type the qualification. | Same as expected. | Pass.
9 | NOT SELECTING BATCH NAME | NORKA / KKEM / KDISC | User should able to get an error message like please select one name from the list. | Same as expected. | Pass.
10 | NOT SELECTING PLACEMENT STATUS | PLACED/ JOB-SEEKING | User should able to get an error message like please select one name from the list. | Not as expected. | Fail. | BUG ID IAJP-48
11 | ENTER VALID PASSWORD | 123aqb$ | User should able to type the valid password. | Same as expected. | Pass.
12 | CLICK SUBMIT |  | User should not able to submit their datas without selecting the details. | Same as expected. | Pass.
Test Case id | TC_09
Test Case Title | Alumni Signup Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Signup Page Validation of Alumni with Null Values in Required Fields
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass
2 | CLICK ON LOGIN AS ALUMNI BUTTON |  | User should able to view the login page with Signup option. | Same as expected. | Pass.
3 | CLICK ON SIGNUP |  | User should able to enter to the signup page. | Same as expected | Pass.
4 | NOT ENTERING NAME |  | User should able to get a message like please provide the name. | Same as expected. | Pass.
5 | NOT ENTERING EMAIL ADDRESS |  | User should able to get a message like please provide the email address . | Same as expected. | Pass.
6 | NOT ENTER VALID PHONE NUMBER |  | User should able to get a message like please provide the phone number. | Same as expected. | Pass.
7 | NOT SELECTING COURSE NAME |  | User should able to get a message like please provide the course name. | Same as expected. | Pass.
8 | NOT ENTERING QUALIFICATION |  | User should able to get a message like please provide the qualification details. | Same as expected. | Pass.
9 | NOT SELECTING BATCH NAME |  | User should able to get a message like please select the batch name. | Same as expected. | Pass.
10 | NOT SELECTING PLACEMENT STATUS |  | User should able to get a message like please provide the placement status. | Same as expected. | Pass.
11 | NOT ENTERING VALID PASSWORD |  | User should able to get a message like please provide the password. | Same as expected. | Pass.
12 | CLICK SUBMIT |  | User should not able to click the submit button. | Same as expected. | Pass.
Test Case id | TC_10
Test Case Title | Alumni Login Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreConditon
Summary | Login Page Validation of Alumni with valid Email Address and Password.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass
2 | CLICK ON LOGIN AS ALUMNI |  | User should able to enter to the login page. | Same as expected. | Pass.
3 | ENTER VALID EMAIL ADDRESS | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address. | Same as expected. | Pass.
4 | ENTER VALID PASSWORD | 12ab$u& | User should able to tye the valid password with atleast two digits,twoletters and one special character. | Same as expected. | Pass.
5 | CLICK SUBMIT |  | User should able to get a login successful message and enter in to the Alumni home page | Same as expected. | Pass.
Test Case id | TC_11
Test Case Title | Alumni Login Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Login Page Validation of Alumni with invalid Email Address and valid Password.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass
2 | CLICK ON LOGIN AS ALUMNI |  | User should able to enter to the login page. | Same as expected. | Pass.
3 | ENTER INVALID EMAIL ADDRESS. | abcccgmail/com abcccAtgmail.com abccc@gmailcom abccc@gmail @gmail | User should able to type the Iinvalid email address. | Same as expected. | Pass.
4 | ENTER VALID PASSWORD | 12ab$u& | User should able to tye the valid password. | Same as expected. | Pass.
5 | CLICK SUBMIT |  | User should get an error message like login unsuccessful due to invalid email address not able to enter to Alumni home page.. | Same as expected. | Pass.
Test Case id | TC_12
Test Case Title | Alumni Login Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Login Page Validation of Alumni with valid Email Address and invalid Password.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass
2 | CLICK ON LOGIN AS ALUMNI |  | User should able to enter to the login page. | Same as expected. | Pass.
3 | ENTER VALID EMAIL ADDRESS. | abccc@gmail.com abccc11@gmail.com | User should able to type the valid email address. | Same as expected. | Pass.
4 | ENTER INVALID PASSWORD | ABCD | User should able to tye the invalid password. | Same as expected. | Pass.
5 | CLICK SUBMIT |  | User should get an error message like login unsuccessful due to invalid password not able to enter to Alumni home page.. | Same as expected. | Pass.
Test Case id | TC_13
Test Case Title | Alumni Login Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Login Page Validation of Alumni with invalid Email Address and invalid Password.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass
2 | CLICK ON LOGIN AS ALUMNI |  | User should able to enter to the login page. | Same as expected. | Pass.
3 | ENTER INVALID EMAIL ADDRESS. | abcccgmail/com abcccAtgmail.com abccc@gmailcom abccc@gmail @gmail | User should able to type the invalid email address. | Same as expected. | Pass.
4 | ENTER INVALID PASSWORD | ABCD | User should able to tye the invalid password. | Same as expected. | Pass.
5 | CLICK SUBMIT |  | User should get an error message invalid email or password and not able to enter to Alumni home page. | Same as expected. | Pass.
Test Case id | TC_14
Test Case Title | Alumni Login Page Validation
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Hasna PV
Test Executed | Hasna PV
PreCondition
Summary | Login Page Validation of Alumni with Email and Password field as Blank.
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | OPEN WEBSITE LINK | https://delightful-earrings-fish.cyclic.app/ | Website should be open | Same as expected. | Pass
2 | CLICK ON LOGIN AS ALUMNI |  | User should able to enter to the login page. | Same as expected. | Pass.
3 | EMAIL ADDRESS AS BLANK. |  | User should able to get a message like this field is required. | Same as expected. | Pass.
4 | PASSWORD AS BLANK. |  | User should able to get a message like this field is required. | Same as expected. | Pass.
5 | CLICK SUBMIT |  | User should not able to click the submit button. | Same as expected. | Pass.
0 | TC_15
Test Case Title | Verify New posts
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Sabu Sebastian
Test Executed | Sabu Sebastian
PreCondition | Website launched, User logged-in, Navigated to the homepage
Summary | Verify New posts displaying on the alumni's profile
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | Verify, the New posts are displayed on the logged-in screen (Homepage) |  | The new posts will be displayed on the logged-in screen (homepage) | Same as expected | Pass
2 | Verify, the Posts displayed are inlcuded with the basic job details such as Job Title, Company Name, and Location |  | The Posts displayed on the page will be inlcuded with the job details such as Job Title, Company Name, and Location | Same as expected | Pass
Test Case id | TC_16
Test Case Title | Verify job search functionality
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Sabu Sebastian
Test Executed | Sabu Sebastian
PreCondition | Website launched, User logged-in, Navigated to the homepage
Summary | Verify job search functionality
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | Click on the search bar input field and enter any keyword | Stack | The user will be able to enter keywords on the search bar input field | Same as expected | Pass
2 | Click on the Search button |  | The system will display the jobs related to the matching keyword | Same as expected | Pass
3 | Click on the back option |  | The application will be redirected to the main page | Same as expected | Pass
4 | Click on the search bar input field and enter any keyword that doesn't exist on any job details | Agriculture | A No jobs found message will be displayed on the application if the keyword entered is not matching with any jobs | The page is buffering and no results shows | Fail | Bug created - Bud ID IAJP-64
5 | Click on the search button without entering any keywords on the search input field |  | The search button will be disabled if the input field doesn't have any keywords | Same as expected | Pass
Test Case id | TC_17
Test Case Title | Verify read more option of the posts
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Sabu Sebastian
Test Executed | Sabu Sebastian
PreCondition | Website launched, User logged-in, Navigated to the homepage
Summary | Verify read more option of the posts displaying in the alumnis profile
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | Click on the Read more option of a job from the Alumni's homepage |  | The application will be redirected to the detailed job details page of the selected job, where user can see the apply job option | The page is started buffering sometimes when clicking on the read more option | Fail | Bug created - Bug Id IAJP-56
2 | Verify the job details page is inlcuded with all the job details such as Job Title, Description, Company Name, Location, and Qualifications. |  | The job details page will be inlcuded with all the job details such as Job Title, Description, Company Name, Location, and Qualifications. | Same as expected | Pass
3 | Verify the user is able to close the detailed job details page and move to the alumni's homepage |  | The user will be able to close the read more page and move to the Alumni's homepage | No page close button to return to the home page | Fail | Bug created - Bug Id IAJP-39
Test Case id | TC_18
Test Case Title | Verify Apply Job functionality
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Sabu Sebastian
Test Executed | Sabu Sebastian
PreCondition | Website launched, User logged-in, Navigated to the homepage
Summary | Verify Alumini's Apply Job functionality with valid details
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | Check the status of the apply button of a job which is posted at least 7 days ago. |  | For jobs that were posted at least seven days ago, the apply button will be disabled. | Same as expected | Pass
2 | Verify the apply button is available for the jobs posted in the past 7 days |  | For jobs that were posted in the past seven days, the apply button will be available. | Same as expected | Pass
3 | Click on the apply button of a job |  | Application will be redirected to the apply job page, and job form will be displayed | Same as expected | Pass
4 | Enter valid details on the apply job form | Enter Your Name: Sabu Sebastian Enter Your Phone Number: 123457894 Enter Your Email Address: test@gmail.com Enter Your Qualification: Bachelor's Degree Enter Your Experience: No prior experience Enter Your Course Name: Software Testing Enter Your Branch Name: Norka 2022 Is You Got Placed Previously ?: No If Then Enter Placed Company Name: (blank) | User will be able to enter valid details on the job apply form and the submit button will be enabled | The Submit button is disabled when leaving 'If Then Enter Placed Company Name' field blank. | Fail | Bug Created - Bug ID IAJP-65
5 | Click on the choose file option |  | The system file manager will be opened | Same as expected | Pass
6 | Pick a file and save |  | The selected file's file name will be displayed on the choose file option tab | Same as expected | Pass
7 | Click on submit button |  | The user will be able to click on submit button and the user will get an alert message regarding successful submission of the job application. | Submit button is disabled when leaving 'If Then Enter Placed Company Name' field blank. | Fail | Bug created on previous steps
8 | Click on the apply button of a job where the user has already submitted application |  | The apply button for the already applied jobs will be disabled in the alumin's page | Apply button is enabled and user is able to submit multiple applications | Fail | Bug Created - Bug ID IAJP-67
Test Case id | TC_19
Test Case Title | Verify Apply Job functionality
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Sabu Sebastian
Test Executed | Sabu Sebastian
PreCondition | Website launched, User logged-in, Navigated to the apply job page
Summary | Verify Apply Job functionality with invalid details
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | Enter invalid details on Name field, and valid details on all other fields and check the submit button status | Enter Your Name: 1111111 Enter Your Phone Number: 123457894 Enter Your Email Address: test@gmail.com Enter Your Qualification: Bachelor's Degree Enter Your Experience: No prior experience Enter Your Course Name: Software Testing Enter Your Branch Name: Norka 2022 Is You Got Placed Previously ?: No If Then Enter Placed Company Name: (blank) | The submit button will be disabled | The submit button is not disabled | Fail | Bug already created
2 | Repeat the above step by enter invalid details on a field, and valid details on all other fields and check the submit button status |  | The submit button will be disabled | The submit button is not disabled for the following invalid details entered cases on the job application form; 1. Enter digits, special characters on the name field 2. Enter characters other than digits on the Mobile number field 3. Enter an invalid format email address on email id field 4. Enter spaces without characters on the fields 5. Space adding before/after character | Fail | Bug Created - Bug Id IAJP-66
Test Case id | TC_20
Test Case Title | Logut option verification
Test Type | Manual/Automation
Test Priority | 0
Test Designed | Sabu Sebastian
Test Executed | Sabu Sebastian
PreConditions | Website launched,user logged-in
Summary | Logut option verification
Steps | Action | Test data | Expected Result | Actual Result | Pass/Fail | Remarks
1 | Click on the Logout Alumni option |  | The user will be logout from the application and redirected to the application's main page | Same as expected | Pass